## Action List
PIR Action Items
Ref # | Recommendtion | Actions | Responsible | Due Date | Completion Date | Complete
1 | Modify the Kick Off meeting agenda to cover use of timesheets. | Update the agenda document | W. Wallace | 2009-04-01 | 2009-04-01 | Yes
2 |  | Brief existing project teams to cover timesheets in their kick off meetings | W. Wallace | 2009-04-15 |  | No
3 | Train Sponsors on their role in the project | Create a training course | H. Tudor | 2009-04-12 | 2009-04-08 | Yes
Yes
No