## Risk Log
Risk Log
Risk No. | Name | Comments | Impact | Probability | Priority | Status | Assigned To | Strategy |  |  | Priority Calculation
1 | If we do not complete the selection by June we will not be able to implement this year. |  | High | Likely | Medium | Open | J. Smith | Mitigate |  | Catastrophic | Medium | High | Critical | Critical
2 | If key people in Sales do not support the new package, we will not be able to implement CRM as stage two. | Some resistance indicated in early workshops | High | Unlikely | Medium | Open | R. Hood | Mitigate | Impact | High | Medium | Medium | High | Critical
[10 empty] | Medium | Low | Medium | Medium | High
[10 empty] | Low | Low | Low | Medium | Medium
[11 empty] | Unlikely | Likely | Highly Likely | Almost Certain
Probability

## Issue Log
Issue Log
Issue No | Description | Date Raised | Raised By | Impact | Priority | Assigned To | Status | Next Review Date | Resolution Date
1 | Unable to find a suitable Project Manager | 2009-02-01 | Sponsor | High | Critical | HR | Open | 2009-02-15 |  | Open | Catastrophic
2 | No clear scope for the project | 2009-02-02 | J. Smith | Med | High | J. Smith | Complete | 2009-02-03 | 2009-02-04 | In Progress | Major
[10 empty] | Complete | Significant
Minor
Status
Open
Complete
Suspended

## Action Log
Action Log
Issue(I) Risk (R) Action(A) | Risk or Action No. | Action No. | Date Raised | Action | Responsible | Due | Status | Resolution Date
Action No.
R | 1 | 1 | 2009-02-01 | Create a schedule for the selection process. Completion by May. | J. Smith | 2009-02-15 | Suspended
I | 1 | 2 | 2009-02-01 | Recruit a Project Manager | HR | 2009-02-20 | Open

## Parameters (hidden)
Impact | Probability | Priority | Risk Status | Risk Action | Status
Catastrophic | Almost Certain | Critical | Submit | Mitigate | Open
High | Highly Likely | High | Assign | Avoid | Complete
Med | Likely | Medium | Open | Accept | Suspended
Low | Unlikely | Low | Resolve | Transfer
Sign Off
Close