## Issue Register
Issue Log
Initiative/ Project | Issue ID | Issue No | Description | Date Raised | Raised By | Status | Impact | Priority | Assigned To | Next Review Date | Actions Taken | Resolution Date
|  | 1 | Unable to find a suitable Project Manager | 2009-02-01 | Sponsor | Open | Major | High | Critical | HR | Passed to HR to recruit a manager | 2009-02-15 | Open | Catastrophic
|  | 2 | No clear scope for the project | 2009-02-02 | J. Smith | Open | Major | Med | High | J. Smith | Define the scope and get agreement from the Steering Committee | 2009-02-12 | In Progress | Major
[13 empty] | Complete | Significant
Minor

## Issue Actions
Action Items
Issue ID | Description | Action | Responsible | Due Date | Completed Date
From Register | From Register