Project Name

Phase Plan - Project Planning

Document History

| Version | Author | Date | Changes |
| --- | --- | --- | --- |
| 0.1 | Neville Turbit | 1 Feb 09 | First draft |

Table of Contents

Current Status	3

Work Breakdown Structure (WBS)	3

Resource Requirements	4

Schedule	4

Key Milestones	4

Risks or Issues	5

Cost	5

# Current Status

Explain the current status of the project.

Example:  Approval has been given to enter a Project Planning Phase and produce a justification in the form of a Project Charter

# Work Breakdown Structure (WBS)

Identify the work required in the phase.  Using a Work Breakdown Structure (WBS) is a useful approach.

Example:

- Prepare for Phase

  - Change Control

  - Risks

  - Procurement

  - Budget Control

- Set Up

  - Risk Log

  - Issue Log

  - Action Log

  - WBS

  - Draft Schedule

  - Final Schedule

- Resources

  - Resource Requirements

  - Agree Resources

  - Define Roles and Responsibilities

- Produce

  - Communications Plan

  - Risk Assessment

  - Quality Plan

  - Costs

  - Benefits

  - Project Charter, Schedule and Project Management Plan

  - Plan for next phase

- Sign off report

  - Distribute to Sponsor and IT Management

  - Discuss the findings

  - Make amendments if necessary

  - Gain sign off

# Resource Requirements

List the skills required in the project and who might be involved in the next phase.  If a resource name is not available, just identify the skills.

Example:

| Role | Skills | Nominee |
| --- | --- | --- |
| Project Manager | Carry out planning and management of a mid sized project | P. Manager |
| Business Analyst | Assist the business to develop requirements. Plan and manage testing and support |  |
| Sponsor | Provide the money for, and executive support to the project | I. Nitiator |

# Schedule

The schedule does not necessarily need to be a Gantt chart.  If a Gantt chart is prepared, attach it to the report.  The following example would suffice.  It should relate to the WBS.  You should also indicate when the phase will start and when it will end.

Example:

Phase Duration:  1 June to 20 June

| Activity | Work | Start | Finish |
| --- | --- | --- | --- |
| Prepare for Phase | 2 days | 1 June | 3 June |
| Set up Logs | 2 days | 2 June | 6 June |
| Resource Planning | 5 days | 7 June | 14 June |
| Etc. |  |  |  |

# Key Milestones

If the Phase is going to take a few weeks to complete, identify Milestones that will determine if the phase is on track.  As a generalisation there should be a milestone each week or at least every two weeks.

Example:

| Milestone | Date |
| --- | --- |
| Logs set up | 6 June |
| Resource Planning Complete | 14 June |
| Etc. |  |

# Risks or Issues

If there are any impediments to the phase being successfully completed, they should be identified.  Once identified, it should be clear how they are to be handled to minimise impact.

| Risk or Issue | Action |
| --- | --- |
| The Process Owner is on a training course for two weeks | Will approach her and arrange a telephone interview |
| Still major disagreement about the following aspect of the Concept. ……………………… | Schedule a meeting next Monday to resolve the problem. If we cannot resolve it, we move forward with two scenarios and explore both. |
| Etc. |  |

# Cost

Identify the cost of completing the phase.

Example:

Cost involved will be the cost of a Business Analyst for 8 days.  At our standard IT charge out rate this is $.....