## Risks
Risk Log
Risk No. | Description | Impact | Probability | Priority | Status | Assigned To | Strategy | Actions
1 | If we do not complete the selection by June we will not be able to implement this year. | High | Likely | Medium | Open | J. Smith | Mitigate | Draw up a plan to complete selection by May | Catastrophic | Almost Certain | Submit | Mitigate | Critical
2 | If key people in Sales do not support the new package, we will not be able to implement CRM as stage two. | High | Unlikely | Medium | Open | R. Hood | Mitigate | Involve Sales Manager in the project. | High | Highly Likely | Assign | Avoid | High
[9 empty] | Med | Likely | Open | Accept | Medium
[9 empty] | Low | Unlikely | Resolve | Transfer | Low
Sign Off
Close