Project Name

Test Strategy

Document History

| Version | Author | Date | Changes |
| --- | --- | --- | --- |
| 0.1 | Neville Turbit | 1 Feb 09 | First draft |

Table of Contents

Purpose	3

Type of Testing	3

Scheduled for	3

Requirements	3

Resource Requirements	3

Location	4

IT Environmental Requirements	4

Equipment Requirements	4

Data Requirements	5

Backup Requirements	5

Restore Requirements	5

Procedures	6

Problem Identification Procedure	6

Defect Rectification Procedure	6

Retesting Procedure	6

Sign-off Test Cases Procedure	7

Acceptance Criteria	7

Testing Software	8

Test Management Software	8

Testing software	8

Performance Testing Software	8

# Purpose

The "Test Strategy" is focused on "how" the testing is to be undertaken.  It details the approach to testing within the project.  Supporting documents are:

- The "Test Scenarios" identifies what is to be tested.  It lists the situations or test scenarios.

- The "Test Scripts" list:

The “Test Scenario” to be tested

The actual information to be entered

The function to be performed

The expected result

The “Test Scenarios” and “Test Scripts” are contained in the Test Plan.

# Type of Testing

Identify the type of testing to be undertaken.

Example:

User Acceptance Testing

# Scheduled for

List the date range of the testing.

Example:

01-Feb-09 to 15-Feb-09

# Requirements

## Resource Requirements

Identify who will be involved in the testing.  If resources have not been nominated, outline the skills required.

Example:

- Testing Manager - J. Smith

- 2 Testers - To be nominated.  The skills required are:

  - Broad understanding of all the processes carried out by the accounts receivable area.

  - Should be familiar with manual processes currently undertaken for reversing payments.

  - Preferably spent time dealing with inquiries from customers over the phone

- Etc.

## Location

Where will the testing take place?

Example:

The meeting room on the 3rd floor will be set up with four PCs and a printer to do the testing.  The test team will work in that location.  The team doing the configuration and customization will be located just outside the meeting room, and will be available to look at any issues as soon as they are raised.

## IT Environmental Requirements

Outline the details of the environment to be used for testing.

Example:

Two test environments will be set up for testing.  The first is to be used by the users to carry out user acceptance testing of the data input and transaction processing.  To access the first area, select “Environment 500” on the security screen.

The second area will be used to test reports.  This will be accessed as "Environment 501".  Security access will need to be arranged through the System Administrator.

The following conditions apply to the environment:

- No more than 5 users need to use the environment concurrently

- Users should have the ability to run month end processing

- Transaction logs need to be maintained for all processing

Etc.

## Equipment Requirements

Identify the equipment required for testing.

Example:

We will require:

- 2 PCs with Windows XP

- 2 PCs with Windows Vista

- All with access to the LAN

- A black and white A4 laser printer

- An A3 colour printer

- Etc.

## Data Requirements

Identify the data to be used for testing.

Example:

"Environment 500" will contain:

- 1000 customers selected at random from our production database (every 2000th customer alphabetically).

- Transaction date ranges between 2007 and 2009 can be used.

- The database has no records for products x and y

## Backup Requirements

Identify how often data backups should be undertaken and who has responsibility for backups.  Also cover how long backups should be retained.

Example:

Backups should occur:

- Nightly

- During the day at the request of the Test Manager

Responsibility for backups is listed below:

- Test Manager responsible for requesting backups at unscheduled times

- Test Manager responsible for delaying or canceling nightly backups

- Operations responsible for completing backups

Nightly backups should be a full backup.  Unscheduled backups should be incremental backups.

## Restore Requirements

Identify how and when a restore should take place.

Example:

The Test Manager will advise Operations if and when a restore is required to either do a complete refresh of the data or restore to a previous backup.

# Procedures

## Problem Identification Procedure

Identify the procedure to be used when a tester finds a suspected defect.  There should be a nominated resource to receive all defects.  In some cases there may be more than one resource e.g. one person for applications problems and one for operational problems.

Example:

| Step | Action |
| --- | --- |
|  | Identify suspected problem |
|  | Refer to Test Manager |
|  | Does the Test Manager validate the defect If yes, go to Step 4 If no, quit |
|  | Fill out a "Defect Logging Form" |
|  | Enter in the "Defect Log" |
|  | Forward to nominated resource for rectification |

## Defect Rectification Procedure

Identify how the defect will be managed once received.  This procedure would normally be under the control of the person or people rectifying the defect.

Example:

| Step | Action |
| --- | --- |
|  | Receive a "Defect Logging Form" |
|  | Schedule the rectification based on the priority |
|  | Allocate the defect for investigation and rectification |
|  | If defect can be reproduced/validated Rectify and test the defect Go to Step 6 |
|  | If defect cannot be reproduced/validated Discuss with Test Manager Go to Step 6 |
|  | Return to Test Manager. |
|  | Update "Defect Log" |

## Retesting Procedure

Identify the procedure for retesting rectified defects.

Example:

| Step | Action |
| --- | --- |
|  | Receive rectified defect |
|  | Discuss possible implications of rectification with the person who carried out the rectification |
|  | Determine the level of retesting required |
|  | Draw up a test plan Or Identify what part of the original test plan will need to be repeated |
|  | Carry out testing |
|  | If testing is successful Update the "Defect Log" by signing off the fix Quit |
|  | If testing is unsuccessful Update the "Defect Logging Form" Return to the nominated person Update the "Defect Log" to show it is once again awaiting rectification |

## Sign-off Test Cases Procedure

Identify the procedure that will be used to sign-off each test case in the testing.  This includes both the testing outlined in the "Test Plan" and testing of defects that have been rectified.

Example:

| Step | Action |
| --- | --- |
|  | Carry out each testing activity in the "Test Plan" using the "Test Scripts". |
|  | If testing successful, go to Step 4 |
|  | If unsuccessful, see procedure for "Problem Identification". |
|  | Sign and date the "Test Script" |

## Acceptance Criteria

Identify how the total testing will be signed off.  This includes all activities in the "Test Plan" and any rectification of defects.

Example:

Testing will be considered successful when the following conditions are met:

- All testing identified in the "Test Plan" has been completed

- No defects classified as priority "Critical" exist

- No defects classified as priority "High" exist

- Less than 3 defects classified as priority "Medium" exist

- Less than 6 defects classified as priority "Low" exist

- Outstanding defects classified, as "Medium" will be returned from rectification within the next 3 working days.

# Testing Software

## Test Management Software

Identify any software that will be used to manage the testing.  This includes the organisation of the activities to be tested, and the management of defects

Example:

We will use "Test Manager" to manage the testing.  Both the test team and applications development will have access and be able to update the status of defects.

## Testing software

If any automated testing software such as WinRunner is to be used, detail the software. Also identify if the software will need to be purchased.

## Performance Testing Software

If any performance testing software is to be used, detail the software.  Also identify if the software will need to be purchased.