Project Name

Phase Plan - Business Process

Document History

| Version | Author | Date | Changes |
| --- | --- | --- | --- |
| 0.1 | Neville Turbit | 1 Feb 09 | First draft |

Table of Contents

Current Status	3

Work Required	3

Resource Requirements	3

Schedule	4

Key Milestones	4

Risks or Issues	5

Cost	5

# Current Status

Explain the current status of the project.

Example:  In the Preliminary Requirements Phase we identified business processes at a high level.  We now will review that work, and expand it to a lower level in order to create the “as is” model.`

# Work Required

Identify the work required in the phase.  Using a Work Breakdown Structure (WBS) is a useful approach.

Example:

- Prepare for Phase

  - Identify work required to map the processes

  - Hold Kick Off Meeting

- Map existing processes

- Identify process impacts

- Map new processes

- Break processes into pre-implementation and post-implementation

- Pre-business processes

  - Prepare training

  - Carry out training

  - Implement

- Produce post-implementation training

- Business Process Report

# Resource Requirements

List the skills required in the project and who might be involved in the next phase.  If a resource name is not available, just identify the skills.

Example:

| Role | Skills | Nominee |
| --- | --- | --- |
| Project Manager | Carry out planning and management of a mid sized project | P. Manager |
| Business Process Modeller | Map the processes |  |
| Sponsor | Provide the money for, and executive support to the project | I. Nitiator |

# Schedule

The schedule does not necessarily need to be a Gantt chart.  If a Gantt chart is prepared, attach it to the report.  The following example would suffice.  It should relate to the WBS.  You should also indicate when the phase will start and when it will end.

Example:

Phase Duration:  1 June to 20 June

| Activity | Work | Start | Finish |
| --- | --- | --- | --- |
| Prepare for Phase | 2 days | 1 June | 3 June |
| Map existing processes | 2 days | 2 June | 6 June |
| Identify process impacts | 5 days | 7 June | 14 June |
| Etc. |  |  |  |

# Key Milestones

If the Phase is going to take a few weeks to complete, identify Milestones that will determine if the phase is on track.  As a generalisation there should be a milestone each week or at least every two weeks.

Example:

| Milestone | Date |
| --- | --- |
| Existing processes mapped | 6 June |
| New processes mapped | 14 June |
| Etc. |  |

# Risks or Issues

If there are any impediments to the phase being successfully completed, they should be identified.  Once identified, it should be clear how they are to be handled to minimise impact.

| Risk or Issue | Action |
| --- | --- |
| The Process Owner is on a training course for two weeks | Will approach her and arrange a telephone interview |
| Still major disagreement about the following aspect of the Concept. ……………………… | Schedule a meeting next Monday to resolve the problem. If we cannot resolve it, we move forward with two scenarios and explore both. |
| Etc. |  |

# Cost

Identify the cost of completing the phase.

Example:

Cost involved will be the cost of a Business Process Analyst for 8 days.  At our standard IT charge out rate this is $.....